ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	5

2.	OBJECTIVES & EXPECTED OUTPUTS	5

2.1.	Overall objective	5

2.2.	Specific objective(s)	6

2.3.	Expected outputs to be achieved by the contractor	6

3.	ASSUMPTIONS & RISKS	7

3.1.	Assumptions underlying the project	7

3.2.	Risks	7

4.	SCOPE OF THE WORK	8

4.1.	General	8

4.2.	Specific work	9

4.3.	Project management	12

5.	LOGISTICS AND TIMING	13

5.1.	Location	13

5.2.	Start date & period of implementation of tasks	13

6.	REQUIREMENTS	14

6.1.	Staff	14

6.2.	Office accommodation	16

6.3.	Facilities to be provided by the contractor	16

6.4.	Equipment	16

7.	REPORTS	16

7.1.	Reporting requirements	16

7.2.	Submission and approval of reports	17

8.	MONITORING AND EVALUATION	17

8.1.	Definition of indicators	17

8.2.	Special requirements	18

# BACKGROUND INFORMATION

## Partner country

Republic of Bulgaria

## Contracting authority

## Directorate “Territorial Cooperation Management”, Ministry of Regional Development and Public Works, Republic of Bulgaria

## Country background

During the 2014-2020 programming period there are three specific bilateral cross-border co-operation Programmes between Bulgaria and EU External Borders’ Partnering Countries that have been implemented with the support of EU financial assistance as well as national co-financing. As a Member State of the European Union since January 1st, 2007 The Republic of Bulgaria has taken over the responsibility for management and control of IPA Cross-border Programmes with Serbia, the Republic of North Macedonia and Türkiye. All programmes are in line with the idea that border regions are often facing disadvantages due to their peripheral geographical locations and relative isolation from national economies. At the same time, the development of European Union’s internal market (along with the four freedoms, namely, free movement of people, goods, services and capital) also brought out the need for the sustainable and balanced development and integration of the whole European territory.

## Current situation in the sector

The cross-border cooperation programmes support European integration processes by establishing cross-border infrastructure of local or regional relevance, coordinating or joining the provision of services in cross-border areas, promoting community integration across borders. In addition, IPA cross-border Programmes are intended to provide assistance to the accession countries in terms of building up and strengthening institutional capacity for managing Structural Financial Instruments in view of their forthcoming EU membership.

Cross-border cooperation component within Instrument for Pre-accession Assistance (IPA) aims at promoting good neighbourly relations, fostering stability, security and prosperity in the mutual interest of all countries concerned, and encouraging their harmonious, balanced and sustainable development.

IPA II is meant to support eligible territories or programme areas in adopting and implementing the political, institutional, legal, administrative, social and economic reforms required so as to help accession countries in a broader context to comply with the European Union’s values and to progressively align to the Union’s rules, standards, policies and practices with a view to membership.

Amongst others, IPA II pursues to achieve some specific objectives including the support for political reforms, support for economic, social and territorial development aiming at smart, sustainable and inclusive growth, strengthening institutional ability at all levels to fulfil membership obligations by supporting progressive alignment with, adoption, implementation and enforcement of the acquis communautaire including the preparation for managing structural instruments and last but not least, strengthening regional integration and territorial cooperation.

For the programming period 2014-2020, the Republic of Bulgaria and its neighbouring IPA beneficiary countries have been jointly implementing:

- Bulgaria – Serbia Interreg- IPA Cross-border Programme 2014-2020;

- Bulgaria – the former Yugoslav Republic Macedonia Interreg-IPA Cross-border Programme 2014-2020;

- Bulgaria – Turkey Interreg- IPA Cross-border Programme 2014-2020.

Bulgaria – Serbia Interreg-IPA Cross-border Programme 2014-2020

Programme’s budget amounts EUR 34 million. The overall objective of the Programme is to strengthen territorial cohesion of the Bulgarian–Serbian cross-border region, its competitiveness and sustainability in its development through cooperation in the economic, social and environmental area.

The selected thematic priorities are structured around three priority axes to reflect the needs and challenges identified in programme area’s analysis, namely:

Priority axis 1 “Sustainable Tourism”

Priority axis 2 “Youths”

Priority axis 3 “Environment”

During the 2014-2020 programming period, still being under implementation, two calls for project proposals have been launched and 106 subsidy contracts were inked at the total budget of EUR 37.7 million (including over-contracting) as 92 projects were completed by December 2022.

For more details, please, visit http://www.ipacbc-bgrs.eu/

Bulgaria – the former Yugoslav Republic of Macedonia Interreg-IPA Cross-border Programme 2014-2020

Programme’s budget amounts to more than EUR 19 million. The overall objective of the Programme is the sustainable development in the cross- border region in support of the wider European cooperation and integration efforts.

The selected thematic priorities are structures around three priority axes to reflect the needs and challenges identified in programme area analysis, namely:

Priority axis 1 “Environment”

Priority axis 2 “Tourism”

Priority axis 3 “Competitiveness”

During 2014-2020 programming period, still being under implementation, two calls for project proposals have been launched and 73 subsidy contracts were inked at the total budget of EUR 20 million (including over-contracting) as 66 projects were completed by December 2022.

For more details, please, visit http://www.ipa-cbc-007.eu/

Bulgaria – Turkey Interreg-IPA Cross-border Programme 2014-2020

Programme’s budget amounts to EUR 29.6 million. The overall strategic goal of the Programme is to achieve a balanced sustainable development built upon the key strengths of the Bulgaria – Türkiye cross-border cooperation area in contribution to stronger European cooperation and integrity.

The selected thematic priorities are structures around two priority axes to reflect the needs and challenges identified in programme area’s analysis, namely:

Priority axis 1 “Environment”

Priority axis 2 “Sustainable tourism”

During 2014-2020 programming period, still being under implementation, two calls for project proposals have been launched and 101 subsidy contracts were signed at the total budget of EUR 31.4 million (including over-contracting) as 97 projects were completed by December 2022.

For more information, please visit: http://www.ipacbc-bgtr.eu/

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective (Impact) to which this action contributes is:

Performance of impact evaluation of  Interreg-IPA Cross-border Programmes 2014-2020, managed by the Republic of Bulgaria moving away from a focus on the absorption of funds to a clearer articulation of the results.

The specific  objectives of this contract are as follows:

1) To perform impact evaluation of the Interreg-IPA Cross-border Programmes 2014-2020, managed by Bulgaria through elaboration of an analysis of the level of achievement of programmes output and result indicators and their compliance with the set programmes’ targets; a thorough analysis of long-term impacts of Programmes’ interventions on the cross-border area, project partners and target groups.

2) To propose recommendations for the implementation of the Programmes for the 2021-2027 period through summarizing lessons learned from Programmes/projects implementation 2014-2020.

The objective of this evaluation is to illustrate the impact of achieved Programmes’ results and effects, as well as the sustainability of achieved results and the effects of communication in relation to the planned objectives.

The evaluation also aims at identifying which are the key challenges and which improvements are necessary for the 2021-2027 programming period.

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

Performed  impact evaluation of the IPA Cross-border Programmes 2014-2020, managed by the Republic of Bulgaria through elaboration of an analysis of the level of achievement of programmes output and result indicators and their compliance with the set programmes’ targets; a thorough analysis of  long-term impacts of Programmes’ interventions on the cross-border area, project partners and target groups.

Proposed recommendations for the Programme implementation in the 2021-2027 period through summarizing lessons learned from Programmes/projects implementation from the 2014-2020 period.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

The following assumptions shall be taken into account during the implementation of the contract:

- Full cooperation between the Contracting authority and the Consultant, including active involvement of the Programmes’ bodies in the implementation of the contract;

- Availability of all necessary administrative and operational documents, data from the MIS system of the respective Programme, results from previous evaluations, etc.

- Support from the Programme stakeholders and target groups when giving feedback on the implementation of the Programmes.

## Risks

In order that the successful implementation of the contract is ensured, the Contractor shall take into account the risks specified below even though some of them are outside the scope of its competences:

- Lack of necessary information;

- Inability to collect, analyse and summarize in short-terms and in details the wide range of information regarding the implementation of the three IPA CBC Programmes;

- Low level of support/response from the relevant stakeholders when giving feedback on the project implementation.

- Health/economic/military restrictions

# SCOPE OF THE WORK

## General

### Description of the assignment

The Impact evaluation shall be focused on capturing the effects of the Interreg-IPA CBC Programmes, managed by the Republic of Bulgaria for the 2014-2020 programming period as regard to their objectives and targets.

In addition, the evaluation will build specific knowledge on the impact and sustainability of the Programmes and will be used as a useful tool for steering a more result-oriented implementation of the Programmes in the 2021-2027 period.

The Contractor shall analyse the long-term impacts of the interventions co-funded by the Interreg-IPA CBC Programmes 2014-2020, managed by the Republic of Bulgaria, and assess their compliance with the set programmes objectives; summarize the lessons learned and propose recommendations for projects development for successful implementation of Interreg IPA-CBC Programmes 2021-2027.

The evaluation shall cover the period from 1 January 2014 to 31 December 2022, taking into account the already carried out midterm evaluation of the programmes. The results from the mid-term evaluation of the three IPA Programmes are available on the following links:

- BG-MK http://www.ipa-cbc-007.eu/documents-implementation-stage-implementation-stage/implementation-evaluation-executive-summary

- BG-TR http://www.ipacbc-bgtr.eu/documents-implementation-stage-news/implementation-evaluation-executive-summary

- BG-RS - http://www.ipacbc-bgrs.eu/documents/-evaluation-executive-summary

### Geographical area to be covered

The geographical area to be covered by the current contact is the eligible programme territory of the three IPA Cross-border Programmes, managed by the Republic of Bulgaria for the 2014-2020 programming period.

### Target groups

- Managing authority

- National authorities in the neighbouring IPA beneficiary countries

- Joint Secretariats

- Beneficiaries

- Other relevant stakeholders (partners at national, regional and local level and in the economic, social, environmental or other spheres), media etc.

## 4.2. Specific work

The Contractor shall achieve the contract results through the tasks, described in the non-exhaustive list below:

            - Collecting data and drawing-up findings concerning Programmes’ results achievement in relation to the targets set for each priority axis.

# The activity contains examination of every Programme implementation and providing evidence of the level of achievement of initially set Programme’s target expressed in qualitative and quantitative terms; estimating the projects achievements in terms of Programmes outputs and results indicators for the respective priority axis and measures/sphere of interventions; defining the main type of beneficiaries and target groups actively involved and/or interested in the programmes implementation, and the preferable  themes of cooperation under the Programmes.

The monitoring of the progress of the result indicators at different stages of programme implementation (2018, 2023) and the comparison with the baseline situation (2014/2015) will provide an important input for the impact evaluation since it will give evidence of changes, both in quantitative and qualitative terms. This will allow getting a clear and impartial perception on progress made and on results achieved by the programme compared to the initial situation as described in the baseline. The information gathered for the needs of result indicators monitoring will also contribute to a more in-depth understanding of the changes achieved and will serve as a valuable basis for the impact evaluation.

This task shall combine desk and field research including visualisation of findings (charts, graphs, maps, presentations etc.) and any other methods for collecting data proposed by the Contractor.

The indicative methods and tools to be applied for the impact evaluation are listed below:

- Desk research and literature reviews (e.g. programme documents, internal procedures, application guide, Programme implementation manual, etc.);

- Data analysis (in particular data collected on output and result indicators);

- Surveys (e.g. addressing project beneficiaries, target groups, experts);

- Focus groups (e.g. with thematic experts);

- Interviews (e.g. with programme bodies, project beneficiaries, other relevant target groups etc.);

- Case studies (e.g. on thematic achievements, target groups involvement, policy impacts, etc.);

Other relevant data for the impact evaluation are available from the monitoring of the funded projects which is uploaded in the MIS. The system also includes all deliverables and outputs from the project implementation as well as reported indicators which constitute a very comprehensive information source for analysing the thematic project achievements. The summarized data from the MIS regarding the level of achievement of the indicators will be provided by the Contracting Authority to the Contractor.

            - Elaborating the impact evaluation of the Interreg- IPA Cross-border Programmes 2014-2020

The main goal of the planned impact evaluation is to assess the effects of the Programmes’ implementation to the cross-border regional development and to analyse the mechanisms producing the impact. The challenges of the impact evaluation clearly lie in distinguishing the effects of programme implementation from the contribution of other external factors (such as other EU co-financed programmes, socio-economic developments, political changes, etc.).

The impact evaluation will be carried out following a theory-based approach, which follows the steps of the programme intervention logic identifying causal links and mechanisms of change. Its main goal is to explain why a given change has occurred and how an intervention has caused that change. This approach mainly produces a qualitative estimate of the impacts.

The impact evaluation covers the Programmes’ priority axes, excluding Technical assistance, and their specific objectives by considering the following guiding principles of theory based impact evaluation:

- Identifying changes: What change can be observed in relation to the objectives of the programme?

- Estimating impacts: To what extent can the observed changes be attributed to the implementation of the programme?

- Understanding impacts and showing what works best in terms of effectiveness and efficiency: What mechanisms of programme implementation have delivered the observed impact?

Considering the above mentioned guiding principles, the following indicative evaluation questions have been drawn for each Programme priority axes (PA) and specific objective (SA).

Bulgaria – the former Yugoslav Republic of Macedonia Interreg-IPA CBC Programme 2014-2020

## Priority axis 1 “Environment”

Specific objective 1.1 “Environmental protection and sustainable use of the common natural resources of the CBC area”

- What change can be observed in the programme area in the level of capacity in environmental protection and sustainable use of common natural resources?

- To what extent has the Programme contributed to the environmental protection and sustainable use of the common natural resources of the cross-border area?

- What are the factors facilitating that contribution? Are there any unintended effects of the programme in this field?

Specific objective 1.2 “Prevention and mitigation of consequences of natural and man-caused disasters of cross-border dimension and impact”

- What change can be observed in the programme area in relation to the joint interventions in the field of prevention and mitigation of consequences of natural and man-caused disasters of cross-border dimension and impact?

- To what extent has the Programme contributed to the improvement of the local capacities in terms of the prevention and mitigation of consequences of natural and man-caused disasters of cross-border dimension and impact?

- What are the factors facilitating that contribution? Are there any unintended effects of the programme in this field?

## Priority axis 2 “Tourism”

Specific objective 2.1 “Enhancing the tourism potential of the region through cooperation initiatives in better preservation and sustainable utilisation of natural and cultural heritage”

- What change can be observed in the level of tourist attractiveness of the cross-border region?

- To what extent has the Programme contributed to the enhancement of the tourism potential of the region through cooperation initiatives in better preservation and sustainable utilization of natural and cultural heritage?

- What are the factors facilitating that contribution? Are there any unintended effects of the programme in this field?

Specific objective 2.2 “Raising the competitiveness of the CBC region's tourism offer”

- What change can be observed in the level of joint and integrated approaches to sustainable tourism development in the border area?

- To what extent has the Programme contributed to raising the competitiveness of the cross-border region's tourism offer?

- What are the factors facilitating that contribution? Are there any unintended effects of the programme in this field?

Specific objective 2.3 “Promoting cooperation among regional actors in the area of sustainable tourism”

- What change can be observed in the level of public awareness regarding sustainable use of natural and cultural heritage and resources?

- To what extent has the Programme contributed to promoting cooperation among regional actors in the area of sustainable tourism?

- What are the factors facilitating that contribution? Are there any unintended effects of the programme in this field?

## Priority axis 3 “Competitiveness”

Specific objective 3.1 “Improving the competitiveness of regional businesses”

- What change can be observed in relation to cross-border business networks created or extended?

- To what extent has the Programme contributed to improvement of the regional businesses competitiveness?

- What are the factors facilitating that contribution? Are there any unintended effects of the programme in this field?

Bulgaria-Turkey Interreg –IPA CBC Programme 2014-2020

## Priority axis 1 “Environment”

Specific objective 1.1 “Preventing and mitigating the consequences of natural and man-made disasters in the cross-border area”

- What change can be observed in the programme area in relation to the level of preparedness to manage emergency situations in the cross-border area?

- To what extent has the Programme contributed to the improvement of the local capacities for preventing and mitigating the consequences of natural and man-made disasters in the cross-border area?

- What are the factors facilitating that contribution? Are there any unintended effects of the programme in this field?

Specific objective 1.2 “Improving the capacity for nature protection, sustainable use and management of common natural resources through cooperation initiatives in the cross-border area”

- What change can be observed in the programme area in relation to the level of capacity for nature protection, sustainable use and management of common natural resources in the cross-border area?

- To what extent has the Programme contributed to the improvement of the capacity for nature protection, sustainable use and management of common natural resources through cooperation initiatives in the cross-border area?

- What are the factors facilitating that contribution? Are there any unintended effects of the programme in this field?

## Priority axis 2 “Sustainable tourism”

Specific objective 2.1 “Increasing the touristic attractiveness of the cross-border area through better utilisation of natural, cultural and historical heritage and related infrastructure”

- What change can be observed in increasing the touristic attractiveness of the cross-border area through better utilisation of natural, cultural and historical heritage and related infrastructure?

- To what extent has the Programme contributed to the increase of the touristic attractiveness of the cross-border region?

- What are the factors facilitating that contribution? Are there any unintended effects of the programme in this field?

Specific objective 2.2 “Increasing the cross-border tourism potential by developing common destinations”

- What change can be observed in the level of joint and integrated approaches to sustainable tourism development in the border area?

- To what extent has the Programme contributed to the increase of the cross-border tourism potential?

- What are the factors facilitating that contribution? Are there any unintended effects of the programme in this field?

Specific objective 2.3 “Increasing networking for development of sustainable tourism through crossborder cooperation initiatives”

- What change can be observed in the level of capacity, awareness and initiatives for sustainable tourism development in the cross-border area?

- To what extent has the Programme contributed to increasing cross-border networking for development of sustainable tourism through cross-border cooperation initiatives?

- What are the factors facilitating that contribution? Are there any unintended effects of the programme in this field?

Bulgaria-Serbia Interreg –IPA CBC Programme 2014-2020

## Priority Axis 1 “Sustainable tourism”

Specific objective 1.1 “Tourist attractiveness: Supporting the development of competitive tourist attractions achieved through cooperation, thus contributing to the diversification of tourist product(s) in the cross-border region”

- What change can be observed in enhancing the tourism attractiveness of the cross-border region in view of diversification of tourist product(s) achieved through cooperation?

- To what extent has the Programme contributed to the increased attractiveness of the region?

- What are the factors facilitating that contribution? Are there any unintended effects of the programme in this field?

Specific objective 1.2 “Cross-border touristic product: Capturing economic benefits from development of natural and cultural heritage in the border area through creating common cross-border touristic destination(s)”

- What change can be observed in capturing economic benefits from development of natural and cultural heritage in the border area through creating common cross-border touristic destination(s)?

- To what extent has the Programme contributed to the increase of joint and integrated approaches to sustainable tourism development in the border area?

- What are the factors facilitating that contribution? Are there any unintended effects of the programme in this field?

Specific objective 1.3 “People-to-people networking: Capitalising the effect of cultural, historical and natural heritage tourism on border communities through common actions”

- What change can be observed in the field of capitalizing the effect of cultural, historical and natural heritage tourism on border communities?

- To what extent has the Programme contributed to the level of community involvement and awareness about sustainable use of cross-border tourist resources?

- What are the factors facilitating that contribution? Are there any unintended effects of the programme in this field?

## Priority Axis 2 “Youths”

Specific objective 2.1 “Skills & entrepreneurship: Supporting the development of attractive environment for advancement of young people in the border region achieved through cooperation”

- What change can be observed in the level of professional and social realisation of young people in the border area?

- To what extent has the Programme contributed to the development of attractive environment for advancement of young people in the border region?

- What are the factors facilitating that contribution? Are there any unintended effects of the programme in this field?

Specific objective 2.2 “People-to-people networking: Promote cooperation initiatives for and with young people, thus enhancing mobility of young people across borders”

- What change can be observed in the level of youth involvement in networks across the border?

- To what extent has the Programme contributed to enhancing mobility of young people across borders?

- What are the factors facilitating that contribution? Are there any unintended effects of the programme in this field?

## Priority Axis 3 “Environment”

Specific objective 3.1 “Joint risk management: To prevent and mitigate the consequences of natural and man-made cross-border disasters”

- What change can be observed in the level of preparedness to manage risks of transnational dimension?

- To what extent has the Programme contributed to prevention and mitigation of the consequences of natural and man-made cross-border disasters?

- What are the factors facilitating that contribution? Are there any unintended effects of the programme in this field?

Specific objective 3.2 “Nature protection: Promoting and enhancing the utilization of common natural resources, as well as stimulating nature protection in the programme area, through joint initiatives across the border”

- What change can be observed in the capacity for nature protection and sustainable use of common natural resources in the border region?

- To what extent has the Programme contributed to nature protection and valorisation of common natural resources in the programme area?

- What are the factors facilitating that contribution? Are there any unintended effects of the programme in this field?

            - Drawing-up recommendations on Programmes and project level which could facilitate the future projects planning and to ensure sustainability of the results.

The Contractor shall propose for each conclusion a corresponding recommendation. The key points of the conclusions will vary in nature but will have to cover aspects of the evaluation questions. The recommendations should be as realistic, operational and pragmatic as possible and presented as a separate final chapter in the Impact Evaluation Report.

The recommendations could be used, on the one hand, at a strategic (planning) level and at the level of the design of the interventions, and, on the other hand, at the level of selection of proper mechanism and approaches of proper implementation.

The Contractor shall also comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en) and use the foreseen events as a tool for dissemination of the Contract results.

## 4.3. Project management

### 4.3.1. Responsible body

The Contracting authority (CA) is the Ministry of Regional Development and Public Works of the Republic of Bulgaria in its capacity of a Managing authority for all three Interreg-IPA Cross-border Programmes between Bulgaria and EU External Borders’ Partnering Countries under implementation during 2014-2020 programming period (Serbia, Republic of North Macedonia and Türkiye). The Contracting authority is responsible for conducting the current tender procedure, signing the service contract and carrying out the overall management and control on the contract implementation.

The Contractor is fully responsible for the quality and timely delivery of the project results, according to the contract provisions. In this respect, the Contractor shall ensure that the specific activities and reports are delivered in time and the quality of those deliverables is in line with the CA requirements.

### 4.3.2. Management structure

The effective management of the project will be ensured by the Contracting authority, Ministry of Regional Development and Public Works of the Republic of Bulgaria, in its capacity of Managing authority for all three IPA Cross-border Programmes between Bulgaria and the Partnering Countries.

### 4.3.3. Facilities to be provided by the contracting authority and/or other parties

No facilities or equipment will be provided by the Contracting authority.

# LOGISTICS AND TIMING

## Location

For the purpose of quality implementation of contract tasks and in order to develop a comprehensive, realistic and coherent impact evaluation, the Consultant should plan visits in the cross-border regions covered by the programmes.

## Start date & period of implementation of tasks

The intended start date is 20.02.2023.  The period of implementation of the contract will be 8 months, but not later than 15.11.2023.

The indicative time schedule for implementation of the assignment is as follows:

| Activity No. (in reference with point 4.2 above) | Description | Month |
| --- | --- | --- |
|  | Kick off meeting with the Contracting authority | 1 |
|  | Delivery of Inception Report | 1 |
| 1 | Collecting data and drawing-up findings | 1-4 |
| 2 | Preparing impact evaluation | 5-6 |
| 3 | Drawing-up recommendations | 7 |
|  | Delivery of Draft Final Report | 8 |
|  | Final Report and contract outputs | 8 |

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

Please, note that key experts participated in contracts for preparation of Interreg - IPA CBC Programmes 2014-2020, managed by the Republic of Bulgaria (publication ref. EuropeAid/133413/D/SER/Multi), are not allowed to be non-key experts under this contract. If a key expert, who participated in contracts for preparation of Interreg - IPA CBC Programmes 2014-2020, managed by the Republic of Bulgaria, has been proposed as a non-key expert under this contract, the corresponding tender will be rejected.

### Key experts

Key experts are not required.

### Other experts, support staff & backstopping

Not applicable.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting authority as part of this service contract or transferred to the CA at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English in one original and one electronic copies:

- Inception Report of maximum 20 pages to be produced after 15 calendar days from the start of implementation. In the report the contractor shall describe e.g. methods to be used, initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme. The contractor should precede with his/her work unless the Contracting authority sends comments on the inception report.

- Draft final report of maximum 20 pages (main text, excluding annexes). The draft final report should be supplemented by electronic version of the draft Impact Evaluation Report containing an overall review of the three Programmes together with replies to the evaluation questions, findings, conclusions and recommendations for corrective actions and for programming 2021-2027 and implementation. This report shall be submitted no later than one month before the end of the period of implementation of tasks.

- Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 15 calendar days after receipt of comments on the draft final report. The Final Report should be supplemented by final Impact Evaluation Report for the three Programmes of maximum 100 pages (hard copy and an electronic version containing both word and .pdf format) and executive summary of maximum of 7 pages (hard copy and an electronic version containing both word and .pdf format). The report shall contain a sufficiently detailed description of the different options to support an informed decision on the conclusions of the impact evaluation. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

- The report referred to above must be submitted to the Contracting authority identified in the contract. The Contracting authority is responsible for approving the reports.

In case comments arise, the Contracting authority sends the report back in 10 working days deadline and the Contractor submits the revised report again in 10 working days. In the absence of comments or approval by the Contracting authority within 10 working days, the reports are deemed to be approved.

# MONITORING AND EVALUATION

## Definition of indicators

The successful implementation of the contract will be assessed on the base of the following indicators of achievement:

- An electronic version and one hard copy of the Impact Evaluation Report delivered.

## The report shall include:

## Executive summary - should be tightly drafted, and usable as a free-standing document. It should be short, not more than five pages. It should focus on the main analytical points, indicate the main conclusions, lessons learned and specific recommendations. Cross-references should be made to the corresponding page or paragraph numbers in the main text that follows.

  - Evaluation purpose

  - Evaluation methodology

  - Intervention description

  - Findings

  - Conclusions (answers to the Evaluation Questions)

  - Recommendations

  - Annexes (e.g. list of people/stakeholders interviewed, key documents consulted, data collection instruments, etc.)

- Inception, draft final and final reports submitted and approved by the Contracting authority.

## Special requirements

- The communication between the Consultant and the Contracting authority must be in writing. The Contracting authority will appoint a contact person for the contract.

A common report incorporating the evaluation of the three programmes

A common report incorporating the evaluation of the three programmes