ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	3

1.5.	Related programmes and other donor activities	5

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	6

2.1.	Overall objective	6

2.2.	Purpose	6

2.3.	Results to be achieved by the Contractor	7

3.	ASSUMPTIONS & RISKS	7

3.1.	Assumptions underlying the project	7

3.2.	Risks	8

4.	SCOPE OF THE WORK	8

4.1.	General	8

4.2.	Specific work	9

4.3.	Project management	12

5.	LOGISTICS AND TIMING	12

5.1.	Location	12

5.2.	Start date & Period of implementation of tasks	12

6.	REQUIREMENTS	16

6.1.	Staff	16

6.2.	Office accommodation	17

6.3.	Facilities to be provided by the Contractor	17

6.4.	Equipment	17

7.	REPORTS	17

7.1.	Reporting requirements	17

7.2.	Submission and approval of reports	18

8.	MONITORING AND EVALUATION	19

8.1.	Definition of indicators	19

8.2.	Special requirements	19

# BACKGROUND INFORMATION

## Partner country

The Republic of Bulgaria, the Republic of Serbia.

## Contracting authority

Territorial Cooperation Management Directorate, Ministry of Regional Development and Public Works, Republic of Bulgaria.

## Country background

The Republic of Bulgaria has been a Member State of the European Union since January 1st, 2007. The Republic of Serbia was granted candidate country status for EU membership in 2012 and accession negotiations were opened in January 2014.

Specific bilateral cross-border co-operation programmes between the Republic of Bulgaria and its neighbouring IPA country, co-financed by EU, have started since 2003. Currently the CBC programme are implemented through shared management and central public authorities of the Republic of Bulgaria are entrusted with the functions of Managing, Certifying and Audit Authorities. The partnering country is represented by Ministry of European Integration of the Republic of Serbia; Department for cross-border and transnational cooperation programmes and cooperation with local and regional authorities and organizations for more efficient use of funds of the Republic of Serbia, acting as National Authority.

The eligible area for the INTERREG-IPA Cross-border Programme Republic of Bulgaria – Republic of Serbia covers a territory of 43 963 km2 (22 822 km2 Bulgarian part and 21 141 km2 Serbian part). The border length between the two countries is 341 km, 315 of which land border and respectively 26 km border on river Timok. There are 5 operating border checkpoints. The common Bulgarian-Serbian border area includes 13 NUTS III regions or equivalents, including 6 Bulgarian districts (Vidin, Montana, Vratsa, Sofia, Pernik and Kyustendil) and 7 Serbian districts (Bor, Zaječar, Nišava, Toplica, Pirot, Jablanica and Pčinja). The programme area is characterized by sparse population, small size of the settlements and a limited number of bigger cities such as Pirot, Niš and Dimitrovgrad (Republic of Serbia) and Vidin, Montana, Kyustendil, Pernik and Vratsa (Republic of Bulgaria). It has a diverse landscape (hills and mountains but also wide plains).

The programme area share many challenges such as a low GDP, negative demographic trends (‘depopulation’), a relatively high level of unemployment, a weak infrastructure and a high vulnerability to natural hazards. All these factors represent major impediments to the cross-border cooperation. At the same time the programme area is rich in natural resources, cultural and historical heritage, which can create new opportunities linked to the exploitation of complementary assets over the borders. The unused potential leaves field for future cooperation among stakeholders and integrated development of the territories.  The Impact Evaluation of the IPA Cross-border Programmes 2007-2013, as well as the midterm evaluation of INTERREG - IPA CBC Programmes 2014-2020, (managed by the Republic of Bulgaria) showed that the programmes delivered wide number and range of outputs, but at the same time it was difficult to establish their effect and the value added achieved by cooperation. In that respect, taking into account the experience from current and previous programming periods a new approach towards the programmes implementation should be envisaged.

## Current situation in the sector

The implementation of the INTERREG CBC programmes for the period of 2021-2027 falls under a new generation of regulations which adhere to new perceptions and principles of how best to address people’s needs. For instance, the new CPR (Common Provisions Regulation) is built on wide experience gained throughout previous programming periods and thus accounts for the following principles in the new one: policy aggregation, simplification, flexibility, proportionality, streamlined and strategic content of the programmes, etc. In light with those principles comes the concentration of the policy objectives (PO) as being reduced from 11 (used in 2014-2020 programme period) to 5 (in 2021-2027 programme period), as follows:

PO1: A smarter Europe - innovative and smart economic transformation.

PO2: A greener, low-carbon Europe.

PO3: A more connected Europe - mobility and regional ICT connectivity.

PO4: A more social Europe - implementing the European Pillar of Social Rights.

PO5: Europe closer to citizens – sustainable and integrated development of urban, rural and coastal areas through local initiatives.

PO 5 is among the five policy objectives which 2021-2027 INTERREG programmes can choose (Art. 4(1) Draft CPR, Art. 14(4) and (5) Draft ETC Regulation). According to the CPR draft regulation, PO5 appropriate to be used to address a functional area with multi-thematic challenges requiring actions not only in one sector, but in an integrated way across different sectors.

The prepared territorial and SWOT analysis for the eligible CBC region, outlines similar economic, social and territorial challenges, needs and potentials of each of them and each could be considered as coherent territory that need to be developed in an integrated way. In that respect, simultaneous and interlinked actions in several sectors are needed and an integrated development under PO5 is the most suitable way forward and according to art. 22 Draft CPR “The Member State shall support integrated territorial development through territorial and local development strategies”. The relatively small and similar as characteristics programme territories, with same multi-thematic challenges and needs, gives the possibility that the whole respective cross-border region could be defined as a functional area, taken into consideration for the preparation of a concrete territorial/local development strategy – to be financed under PO5 of each of the two programmes.

Lessons learned from current and previous programming periods show that for avoiding uncoordinated, dot-like investments, a more integrated territorial approach is desirable, based on the needs and competitive advantages of the CBC region. For the last two programming periods the limited resources of the programmes were directed to scattered sectoral investments based on open calls where coordination with the local territorial needs was not sufficient. A new approach was supported by the local stakeholders during the regional consultations held for all IPA programmes, proposing dedicated measures to be applied in order the full potential of the region to be exploited. In that respect the local stakeholders declared their readiness to actively participate in the different stages of the preparation and implementation of the respective territorial strategy, envisaging integrated measures for fostering the territorial development and in particular local economy.

## Related programmes and other donor activities

•	Cross-border co-operation between the Republic of Bulgaria and Republic of Serbia and Montenegro started in 2003 under the EU External border initiative with allocation of 0.3 million EUR for project preparation facility;

•	The Joint Programming Document under the Neighbourhood Programme between the Republic of Bulgaria and Republic of Serbia and Montenegro 2004-2006 amounting 11 million EUR EU contribution for the three year period;

•	Bulgaria - Serbia IPA Cross-border Programme 2007-2013 amounting slightly above 31 million EUR EU contribution for the seven year period;

•	South East Europe Transnational Cooperation Programme 2007 – 2013;

•	Danube Transnational Cooperation Programme 2014-2020;

•	The present INTERREG-IPA Cross-border Programme Bulgaria – Serbia 2014-2020 amounting almost 29 million EUR EU contribution for the seven year period

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of this contract is as follows:

To elaborate multiannual Strategy for Integrated Territorial Development, covering the period 2021-2027, with the aim to meet the needs of the INTERREG - IPA CB cooperation programme 2021 -2027 between the Republic of Bulgaria and the Republic Serbia to contribute to a sustainable economic development of the respective region. The implementation of the measures of the Territorial Strategy shall be conducted under the scope of PO5 “Europe Closer to Citizens”.

## Purpose

The purposes of this contract are as follows:

- To support the local stakeholders from the respective CBC region in the elaboration of a Territorial strategy for integrated measures, including identification of functional area/s within the cross-border region, strategy governance and proposal of the list of operations and potential beneficiaries that might be financed under the INTERREG - IPA CBC programme 2021 - 2027 between the Republic of Bulgaria the Republic of Serbia. The strategy to be prepared in compliance with the legal framework taking into account the specificities of the programme area and respecting the principle of multi-level governance;

- To coordinate the preparation of  the territorial strategy in a wide consultative process with the local stakeholders from the CBC region of the respective programme;

- To present the draft Integrated Territorial strategy for the programme at various events (Joint Working Group/Joint Monitoring Committee/Task force group meetings, regional consultations, other).

## Results to be achieved by the contractor

- Final draft of the Integrated Territorial strategy for integrated measures, including identified functional area/s, strategy governance, indicators for implementation and proposal of the list of operations that might be financed under the INTERREG - IPA CBC cooperation programme 2021 -2027 between Republic of Bulgaria and Republic of Serbia in English, Bulgarian and Serbian language;

Regional consultations during the strategy elaboration carried out across the geographical area covered by the strategy;

Draft Territorial strategy presented at relevant events (regional consultations, Joint Working Group/ Joint Monitoring Committee/Task force group meetings, other);

Summary of the Territorial strategy in English, Bulgarian and Serbian language; (for future information campaigns).

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

INTERREG Regulatory framework for 2021 – 2027 period is at place;

Commitment of the stakeholders of Bulgaria and Serbia for applying an integrated approach;

Active involvement of the local stakeholders in the strategy preparation including participation in regional consultations and other events;

Recognition of the strategy ownership by the respective stakeholders.

## Risks

Late issuing of the relevant legislation by the Commission might influence the timeframe, as well as the content of the present task.

Lack of clear assignment of functions related to Strategy implementation.

# SCOPE OF THE WORK

## General

### Description of the assignment

The Consultant has to support the respective regional stakeholders while elaborating the Territorial/local development strategy (covering the period 2021-2027) for integrated measures, including identification of functional area/s, strategy governance, priority/ies, possible investments in areas of economic development, sustainable tourism and culture, as well as other areas with an effect on territorial development and cohesion and proposal of the list of operations that might be financed under the INTERREG - IPA CBC programmes 2021 -2027 between Republic of Bulgaria and the Republic of Serbia. The Territorial strategy should be elaborated in line with the relevant EU regulations ( art. 22 & 23 of the draft CPR and art. 20 of the draft INTERREG Regulation), as well as INTERACT Publication – Bringing territoriality into INTERREG - Policy Objective 5, 18 June 2020. It should be drawn up under the responsibility of the relevant urban, local, regional authorities/bodies. The geographical area to be covered by the respective strategy has to be identified in close coordination with the local stakeholders and the programme structures and an analysis of its development needs and potentials shall be held. The Consultant should elaborate the strategy taking into account the provisions of the relevant EU and national legislation, as well as the existing national, regional and local strategic documents. The strategy should outline the expected contribution to macro-regional and sea-basin strategies, where appropriate.

During the accomplishment of the task the following principles have to be applied by the Consultant:

- Ensuring multi-level governance by involving all competent levels (following a bottom up regional approach in close coordination with the programme structures), respecting the partnership principle.

- Focusing on the cross-border dimension through identifying joint challenges and needs to be tackled (rather than presenting general characteristics and development objectives).

- Horizontal principles as set out in art. 3 the Treaty on EU, aiming at promoting equality between men and women and non-discrimination.

### Geographical area to be covered

During the assignment, the Contractor is going to perform the tasks in Sofia and when necessary in the eligible areas of each INTERREG - IPA CBC Programme in which Bulgaria participates.

### Target groups

Managing Authority, National Authority, Joint Working Group/Monitoring Committee, relevant urban, local, regional authorities/bodies/stakeholders in the participating countries.

## Specific work

The contract results will be achieved through the tasks described in the non-exhaustive list below.

- Setting up a Task force group of relevant regional and local authorities and bodies, as well as other local stakeholders, that will be responsible for the preparation of the strategy.

- Identifying, in close coordination with the Task force group, the geographical area to be covered by the strategy. The area should have a high degree of interactions and interdependencies, where simultaneous actions in different sectors are necessary for their future development (economy, tourism, education, employment, transport, business support etc.).

- Preparing the analysis of the development needs and potentials of the territories covered by the strategy, based on which the key spheres of intervention are identified that will be addressed in the strategy, in close coordination with the Task force group.

- Preparing the description of an integrated approach to address the identified development needs, potential of the region.

4.1 Defining / establishing the strategic context and methodology.

This activity will include establishing the methodology for developing of the strategy, taking into consideration existing strategic documents at European, national, regional and local level. The methodology shall describe the process and appropriate tools for each stage / activity of the development of the strategy.

  - Development of the strategy, including vision and prioritization of interventions. Based on the results from the previous stages, this one will include establishing of the strategic and specific objectives, as well as prioritising measures and interventions (which shall be SMART – specific, measurable, attainable, relevant and time-bound).

  - Preparing a description of the involvement of partners/stakeholders in the preparation and in implementation of the strategy, including the roles and responsibilities of the various parties taking into consideration the multilevel governance principle.

  - Development of the methodology for implementation, monitoring and evaluation of the strategy. The activity includes establishing future responsibilities for the strategy implementation, methodology for monitoring and evaluation of the implementation, defining output and result indicators for the implementation of the strategy.

  - Preparation, in close coordination with the Task force group, of a methodology for and establishment of a long list of operations that might be supported, based on mapping of possible interventions for integrated economic and social development, cultural and natural heritage preservation, sustainable tourism etc., as well as identifying target groups and potential beneficiaries. The operations from the list should be grouped, prioritised and time-bound (based on a transparent and clear methodology and selection criteria).

  - Preparation of criteria for selection and establishing of a short list of operations that might be supported under the respective INTERREG - IPA CBC Programme 2021-2027).

  - Shaping the action plan of the respective 7-year strategy implementation, as well as of the shortlisted operations to be supported by the INTERREG - IPA CBC Programme 2021-2027. During this stage, the timeframe for the implementation of the envisaged measures in order to accomplish the strategy objectives will be established.

The Task force group will be actively involved in the coordination, review and approval of all stages in the strategy elaboration.

- Presenting the final draft of the Territorial strategy at various events (Joint Working Group/Joint Monitoring Committee meetings, regional consultations, other) ensuring wide publicity.

- Reflecting in the final draft of the Territorial strategy the comments and remarks received during the consultation and approval procedures, as well as taking into consideration the outcomes from the Strategic Environmental Assessments (SEA).

- Preparing respective versions of territorial strategy after task 4.4, 4.7 and 6 in English, Bulgarian and Serbian language and summary of the final draft of the territorial strategies after task 6 in English, Bulgarian and Serbian language.

The Consultant must observe the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project (see https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en). Particular attention should be given to ensuring the sustainability and dissemination of results.

Where appropriate and necessary the Consultant shall provide maps, diagrams, charts, etc. giving a better visualisation of the strategy. The maps, diagrams and any additional supporting graphical content should be presented as separate graphic files in appropriate format which will allow further use by the Contracting authority.

The Consultant shall take into consideration the above mentioned specific tasks and requirements while preparing Annex III Organisation and Methodology as part of the technical offer. The Consultant must strictly follow the template (Annex III) from the Tender Dossier and prepare it in a manner demonstrating clear understanding of the contract.

## Project management

### Responsible body

The Contracting Authority (CA) is the Territorial Cooperation Management Directorate within the Ministry of Regional Development and Public Works of the Republic of Bulgaria, in its capacity of Managing Authority for INTERREG – IPA Cross-border Programmes 2014-2020 and is responsible for conducting the current tender procedure, and for signing the service contract

### Management structure

The effective management of the project will be ensured by the Contracting Authority / Managing Authority, in close coordination with the National Authority, Joint Secretariat and Task force group of the INTERREG IPA CBC Bulgaria – Serbia programme.

### Facilities to be provided by the contracting authority and/or other parties

No facilities or equipment will be provided by the Contracting Authority.

# LOGISTICS AND TIMING

## Location

The tasks related to the elaboration of the Integrated Territorial strategy shall be undertaken mainly at the seat of the Consultant. Meetings shall be organised in Sofia (at the premises of the Contracting Authority) and at various locations within the programme area of each programme in accordance with the time frame or in on-line mode.

## Start date & period of implementation of tasks

The intended start date is 25.02.2021 and the period of implementation of the contract will be 12 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

The indicative time schedule for the preparation of the Territorial strategy, is as follows:

|  | Description | Months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | I-st |  |  |  | II-nd |  |  |  | III-rd |  |  |  | IV-th |  |  |  | V-th |  |  |  | VI-th |  |  |  | VII-th |  |  |  | VIII-th |  |  |  | IX-th |  |  |  | X-th |  |  |  | XI-th |  |  |  | XII-th |  |  |  |
|  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
|  | Start of the project – Upon contract signature |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Kick off meeting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Preparation of a detailed work plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Presenting the Inception Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Setting up a Task force group regional and local authorities and bodies, as well as other local stakeholders, that will be responsible for the preparation of the strategy. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Identifying, in close coordination with the Task force group, the geographical area to be covered by the strategy. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Preparing the analysis of the development needs and potential of the territories covered by the strategy. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Review and approval by the Task force group of step 2 and 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Preparing the description of an integrated approach to address the identified development needs and the potential of the region. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.1 Defining / establishing the strategic context and methodology |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.2. Development of the strategy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.3 Preparing a description of the involvement of partners/stakeholders in the preparation and in implementation of the strategy, taking into consideration the multilevel governance principle |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.4. Development of the methodology for implementation, monitoring and evaluation of the strategy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Presentation of the Territorial strategy for the programme – regional consultations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 | Review and approval by the Task force group of step 4.2, 4.3, 4.4. and 4.5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Interim Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.5. Preparation of a long list of operations that might be supported |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.6. Preparation of a short list of operations that might be supported |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4.7. Shaping the action plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 | Presentation of the list of operations and action plan for the programme – regional consultations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 | Review and approval by the Task force group of step 4.6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Strategic Environmental Assessment (carried out by another independent consultant) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 | Presentation of the Territorial strategъat various events |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Draft Final Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 | Reflecting in the final draft of the Territorial strategy the comments and remarks received during the consultation and approval procedures, incl. SEA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 | Respective version of the territorial strategy in English, Bulgarian and Serbian language |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13 | Summaries in English, Bulgarian and Serbian language |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Final Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified and with the official permission of the administration when necessary. The justification and official permission should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

No key experts are required

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The contractor shall select and hire other experts as required according to the needs. The selection procedures used by the contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

Expert 1: Team leader

General professional experience

- preferably 5 years’ experience but a minimum of 3 years required in fields related to elaboration of strategic documents/strategies;

Specific professional experience

- Experience as a Team Leader in projects.

Expert 2: Senior analyst for territorial strategy between Republic of Bulgaria and Republic of Serbia

General professional experience

- preferably 3 years’ experience but a minimum of 2 years required in fields related to elaboration of strategic documents/strategies;

Specific professional experience

- Experience in activities related to elaboration of strategic documents/strategies.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English in one original and in electronic version copies:

- Inception Report of maximum 12 pages to be produced after one week, from the start of implementation. In the report the contractor shall describe e.g. initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel. The contractor should proceed with his/her work unless the contracting authority sends comments on the inception report.

- Interim report of maximum 25 pages to be produced at the beginning of 4th month from the start of implementation. In the report the contractor shall describe e.g. recent findings, progress in collecting data, any difficulties encountered and to present as annexes the draft versions of the strategy in English, Bulgarian and Serbian language. The contractor should proceed with his/her work unless the contracting authority sends comments on the interim report.

- Draft final report of maximum 50 pages (main text, excluding annexes). The draft final report should be supplemented by an electronic version of the draft Territorial strategy for the programme. The strategy should contain vision, functional area/s, strategy governance, established strategic and specific objectives, prioritised measures and interventions, possible investments in the field of sustainable tourism and culture, as well as other areas with an effect on economic development and cohesion, a proposal of the list of operations that might be supported, identified target groups and potential beneficiaries, shaped action plan and developed methodologies for implementation, monitoring and evaluation of the strategy, including output and result indicators for the implementation of the strategy.

- This report shall be submitted no later than one month before the end of the period of implementation of tasks.

Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 10 days after receipt of comments on the draft final report. The Final report shall be maximum 50 pages. The Final Report should be supplemented by final draft of the Territorial strategy for the programme of maximum 200 pages (hard copies and an electronic version containing both word and pdf. format) and summaries of the territorial strategy of maximum 15 pages (hard copies and an electronic version containing both word and pdf. format) in English, Bulgarian and Serbian language. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports. The reports must be written in English.

# MONITORING AND EVALUATION

## Definition of indicators

The successful implementation of the contract will be assessed on the base of the following indicators of achievement:

- An electronic version and hard copy of the final draft of each Territorial strategy in English, Bulgarian and Serbian languages;

- Presented Territorial strategy for each programme at various events (respective Joint Working Group/Joint Monitoring Committee meetings, regional consultations, other), ensured wide publicity;

- Inception, draft final and final reports submitted and approved by the Contracting Authority;

- Identified relevant regional and local authorities and bodies, as well as other local stakeholders;

- Prepared list of operations based on mapping of possible interventions for integrated economic and social development, cultural and natural heritage preservation, sustainable tourism etc., as well as identifying target groups and potential beneficiaries;

- An electronic version of Summary of the Territorial strategies in English, Bulgarian and Serbian language.

## Special requirements

During implementation of the contract, all national and regional anti-epidemiological measures imposed by the authorities must be respected.

Hereinafter referred to as Territorial Strategies

http://www.interact-eu.net/library#2959-publication-bringing-territoriality-interreg-policy-objective-5

Based on input from the programme bodies

including exploring measures for economic development, sustainable tourism and culture, etc.

based on the approved logic of interventions the programme will dedicate 55 % of its total budget to the strategy, and 40% of the strategy budget to investments in sustainable tourism and culture