ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	6

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	6

2.1.	Overall objective	6

2.2.	Purpose	7

2.3.	Results to be achieved by the Contractor	7

3.	ASSUMPTIONS & RISKS	8

3.1.	Assumptions underlying the project	8

3.2.	Risks	8

4.	SCOPE OF THE WORK	8

4.1.	General	8

4.2.	Specific work	9

4.3.	Project management	11

5.	LOGISTICS AND TIMING	12

5.1.	Location	12

5.2.	Start date & period of implementation of tasks	12

6.	REQUIREMENTS	14

6.1.	Staff	14

6.2.	Office accommodation	16

6.3.	Facilities to be provided by the Contractor	16

6.4.	Equipment	16

7.	REPORTS	16

7.1.	Reporting requirements	16

7.2.	Submission and approval of reports	18

8.	MONITORING AND EVALUATION	19

8.1.	Definition of indicators	19

8.2.	Special requirements	19

# BACKGROUND INFORMATION

## Partner country

The Republic of Bulgaria and the Republic of North Macedonia

## Contracting authority

Territorial Cooperation Management Directorate, Ministry of Regional Development and Public Works, Republic of Bulgaria

## Country background

The Republic of Bulgaria has been a Member State of the European Union since January 1st, 2007. The Republic of North Macedonia was granted candidate country status for EU membership in 2005.

Specific bilateral cross-border co-operation programmes between the Republic of Bulgaria and the Republic of North Macedonia, co-financed by EU, have started since 2003. Currently the CBC programmes are implemented through shared management and central public authorities of the Republic of Bulgaria are entrusted with the functions of Managing, Certifying and Audit Authorities. The Republic of North Macedonia is represented by the Ministry for Local Self-government, acting as National Authority.

The eligible area for the INTERREG-IPA III Cross-border Programme between the Republic of Bulgaria and the Republic of North Macedonia covers a territory of 18 087 km2 (9 496 km2 Bulgarian part and 8 591 km2 RNM part). The border is 165 km long, with 3 operating border crossing points. Situated in the south-eastern part of Europe, the border area between Republic of Bulgaria and Republic of North Macedonia has a favourable location. The programme area comprises the 2 districts in the Republic of Bulgaria (Kyustendil and Blagoevgrad) and the three NUTS III equivalent regions in the Republic of North Macedonia (North-East, East and South-East). More than half of the programme area is mountainous with forests occupying over 40% of the territory. There is a concentration of population, economic and social activities in several regional centres, in particular Blagoevgrad and Kyustendil (on the side of the Republic of Bulgaria) as well as in Kumanovo, Shtip and Strumica (on the side of the Republic of North Macedonia). There are also sparsely populated rural and peripheral areas in the mountains closer to the border.

## Current situation in the sector

The implementation of the INTERREG-IPA III CBC Programmes for the period of 2021-2027 falls under a new generation of regulations which adhere to new perceptions and principles of how best to address people’s needs. For instance, the new CPR (Common Provisions Regulation) is built on wide experience gained throughout previous programming periods and thus accounts for the following principles in the new one: policy aggregation, simplification, flexibility, proportionality, streamlined and strategic content of the programmes, etc. In light with those principles comes the concentration of the policy objectives (PO) as being reduced from 11 (used in 2014-2020 programme period) to 5 (in 2021-2027 programme period) including two Interreg specific objectives, as follows:

PO1: A smarter Europe - innovative and smart economic transformation;

PO2: A greener, low-carbon Europe;

PO3: A more connected Europe - mobility and regional ICT connectivity;

PO4: A more social Europe - implementing the European Pillar of Social Rights;

PO5: Europe closer to citizens – sustainable and integrated development of all types of territories;

INTERREG specific objective 1 (ISO 1): A better cooperation governance;

INTERREG specific objective 2 (ISO 2): A safer and more secure Europe.

The administrative, thematic and financial implementation of the INTERREG-IPA III CBC Programme is guided by the following EU regulations, being however not yet adopted by the time of publishing this tender procedure:

(1) Proposal for a Regulation of the European Parliament and of the Council, (2018/0196 (COD)), laying down common provisions on the European Regional Development Fund, the European Social Fund Plus, the Cohesion Fund, and the European Maritime and Fisheries Fund and financial rules for those and for the Asylum and Migration Fund, the Internal Security Fund and the Border Management and Visa Instrument – in short CPR Regulation;

(2) Proposal for a Regulation of the European Parliament and of the Council (2018/0197 (COD)) on the European Regional Development Fund and on the Cohesion Fund - in short ERDF regulation;

(3) Proposal for a Regulation of the European Parliament and of the Council (2018/0199 (COD)) on specific provisions for the European territorial cooperation goal (INTERREG) supported by the European Regional Development Fund and external financing instruments – in short ETC Regulation

According to art. 15, (1) of the ETC Regulation, the EU financial support to INTERREG-IPA III CBC Programmes shall be allocated on a maximum of three out of five policy objectives listed above. Currently, the thematic concentration the INTERREG-IPA III CBC 2021-2027 between the Republic of Bulgaria and the Republic of North Macedonia Programme (INTERREG-IPA III CBC Programme) includes the following policy objectives:

CBC programme between the Republic of Bulgaria and the Republic of North Macedonia

PO 2 “A greener, low-carbon Europe” Specific objective: Enhancing protection and preservation of nature, biodiversity, and green infrastructure, including in urban areas, and reducing all forms of pollution

PO 5 “Europe closer to citizens” Specific objective: Fostering the integrated and inclusive social, economic and environmental development, culture, natural heritage, sustainable tourism and security in all types of territories

PO 3 A more connected Europe - mobility and regional ICT connectivity Specific objective: Developing sustainable, climate resilient, intelligent and intermodal national, regional and local mobility, including improved access to TEN-T and cross-border mobility

Potential project promoters under the programme include public institutions, MSMEs, NGOs, R&D, academic, training and social institutions.

It is important to note that the development of the INTERREG-IPA III CBC Programme is still in progress. However, the first draft version shall be completed and presented to the selected Contractor upon entering this contract into force. The Contractor shall take into account that possible changes in the draft CBC programme may take place any time before the expiration of the contract. If such changes occur, the Contractor must reflect them in the contract outputs accordingly and in due time.

The programme includes PO5 “Europe closer to citizens”, whose implementation is bound with elaboration of Cross border Strategy for Integrated Territorial Development (Territorial Strategy), as regulated in art. 22 and art. 23 of the CPR Regulation. At the time of publishing this tender, the development of the strategy is on-going and first drafts is expected by end of April 2021.

Potential stakeholders under the implementation of the Territorial Strategy are all types of regional and local actors who take active part in the local economic development, including Regional Development Councils whose scope of work, composition, roles and responsibilities are specified in the recently adopted (as of August 2020) new Regulations for the implementation of the Regional Development Act.

In accordance with art. 85 (1) of the Bulgarian Environmental Protection Act (EPA), the start of the INTERREG-IPA III CBC Programme must be preceded by an assessment of the effects of the individual programme and its Territorial strategy on the environment. Hereinafter, are presented the minimum components of the legal and instructional framework that regulates the implementation of this contract in correspondence to the need of conducting environmental assessment:

- EU regulations and directives:

- Directive 2001/42/EC of the European Parliament and of the Council of 27 June 2001 on the assessment of the effects of certain plans and programmes on the environment (SEA Directive);

- Council Directive 92/43/EEC of 21 May 1992 on the conservation of natural habitats and of wild fauna and flora;

- Directive 2011/92/EU of the European Parliament and of the Council of 13 December 2011on the assessment of the effects of certain public and private projects on the environment;

EU guidelines:

- Guidance document on monitoring and evaluation; concepts and recommendations (as of March 2014, revised version in 2018);

- Guidance Document on Evaluation Plans (as of February 2015);

- Tools and Methods Series, Guidelines No 6: Integrating the environment and climate change into EU international cooperation and development (as of February 2016)

UN Conventions

- UN ECE Convention on Environmental Impact Assessment in a Transboundary Context;

- Protocol on Strategic Environmental Assessment to the Convention on Environmental Impact; Assessment in a Transboundary Context

- UN Convention on Biological Diversity;

National legal context:

- Environmental Protection Act and Biological Diversity Act;

- Ordinance of the Ministry of Environment and Water on the conditions and the order for implementing environmental assessment of plans and programs;

- Ordinance of the Ministry of Environment and Water on the conditions and procedures for assessment of the compliance of plans, programs, projects and investment proposals with the object and purposes of conservation of protected areas;

- Regional Development Act, Regulations for the implementation of the Regional Development Act

- Currently, an update of the national strategic documents for the period of 2021-2027 has been undergoing. Their amendment must be taken into account by the Contractor when implementing the contract. These are: (1) The National Development Programme: BULGARIA 2030; (2) the National Regional Development Strategy of the Republic of Bulgaria 2012-2022; (3) the National Concept for Spatial Development of the Republic of Bulgaria for the period 2013 – 2025; (4) Integrated Territorial Strategies for Development of each of the NUTS 2 regions in Bulgaria for 2021-2027; (5) Environmental-related sectoral documents.

In the course of the contract implementation, the Contractor should monitor possible amendments of the legal and instructional documents and reflect them in the contract outputs accordingly and in due time. Furthermore, the Contractor shall identify corresponding national documents of the partnering country (Republic of North Macedonia) and provide for their adequate and comprehensive reflection in the contract outputs.

## Related programmes and other donor activities

- PHARE and CARDS cross-border activities until 2006 including PHARE External Border Initiative in 2003 focused on two projects for Bulgaria – the former Yugoslav Republic of Macedonia and Neighbourhood Programme the Republic of Bulgaria - the former Yugoslav Republic of Macedonia 2004-2006.

- Bulgaria – the former Yugoslav Republic of Macedonia IPA I Cross-border Programme 2007 – 2013 amounting almost 18 million EUR EU contribution for the seven year period.

- South East Europe Transnational Cooperation Programme 2007 – 2013.

- The present INTERREG-IPA II Cross-border Programme between Republic of Bulgaria and Republic of North Macedonia 2014-2020 amounting 16.5 million EUR EU contribution for the seven year period.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part, is as follows:

To ensure a high level of protection and preservation of the environment, as well as to achieve environmental compliance in the process of preparation and approval of the INTERREG-IPA III Cross-border Programme 2021-2027 between the Republic of Bulgaria and the Republic of North Macedonia and associated with it Cross-border Strategy for Integrated Territorial Development under the INTERREG-IPA III Cross-border Programme 2021-2027 between the Republic of Bulgaria and the Republic of North Macedonia.

## Purpose

The purposes of this contract are as follows:

- To ensure coherence and compatibility of the developing INTERREG-IPA III CBC Programme and the Cross-border Strategy for Integrated Territorial Development with the environmental legal acts and standards for the period of 2021-2027;

- To ensure the contribution of the developing INTERREG-IPA III CBC Programme and the Cross-border Strategy for Integrated Territorial Development to the protection of the environment and protected areas;

- To provide for integration of environmental concerns in the preparation of the INTERREG-IPA III CBC programme and the Cross-border Strategy for Integrated Territorial Development and to ensure a higher level of environmental protection and sustainable development in the cross-border areas.

## Results to be achieved by the Contractor

- 2 draft Environmental Assessment Reports (EAR) – one for INTERREG-IPA III CBC Programme and one for Cross-border Strategy for Integrated Territorial Development that are fully compliant with the relevant legal framework - all in Bulgarian and in English. Each report shall be accompanied by a non-technical summary of the information provided in the respective EAR in both languages in compliance with art. 17 (3) of the Ordinance of the Ministry of Environment and Water on the conditions and the order for implementing environmental assessment of plans and programs;

- results of the regional consultations (one for INTERREG-IPA III CBC Programme and one for the Territorial Strategy) reflected in the EARs;

- 2 compliance assessment reports - of  the INTERREG-IPA III CBC Programme and of the Cross-border Strategy for Integrated Territorial Development (two compliance assessment reports in total) in accordance with the requirements of the Ordinance of the Ministry of Environment and Water on the conditions and procedures for assessment of the compliance of plans, programs, projects and investment proposals with the object and purposes of conservation of protected areas – only if it is deemed necessary by the competent authority (the Minister of Environment and Water);

- Opinion/s on the environmental assessment of the INTERREG-IPA III CBC Programme and of the Cross-border Strategy for Integrated Territorial Development issued in accordance with the Ordinance for implementing environmental assessment of plans and programs;

- 2 final Environmental Assessment Reports – one for INTERREG-IPA III CBC programme and one for the Cross-border Strategy for Integrated Territorial Development in English and Bulgarian;

Summary of the two final Environmental Assessment Reports in English and Bulgarian (for public information purposes)

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- The implementation of the contract will take place in a dynamic context of the IINTERREG-IPA III CBC programming for the period 2021-2027. In parallel with the work on this contract, it is expected that the main European and Bulgarian legal, strategic and planning documents regulating the implementation of the European funds for the next programming period, will be further developed, updated and adopted. The Contractor must ensure that any changes occurred, until the expiration of the contract, in the relevant legal, strategic and planning framework shall be reflected in its work accordingly and in due time;

- If unforeseen circumstances obstruct the timely presentation of the draft version of the INTERREG-IPA III CBC Programme to the Contractor, the version will be substituted with the Programme Intervention Logic document which present the logic links between key programme parameters and their justification.

## Risks

- Changes in the legal, strategic and planning framework of the programming for 2021-2027, that may lead to modifications of the draft version of the the INTERREG-IPA III CBC Programme and the Cross-border Strategy for Integrated Territorial Development, may occur any time before this contract expires;

- Lack of synchronization between the production of the first draft versions of the INTERREG-IPA III CBC Programme and the Cross-border Strategy for Integrated Territorial Development;

# SCOPE OF THE WORK

## General

### Description of the assignment

This assignment relates to the implementation of Environmental Assessment (EA) of the INTERREG-IPA III CBC Programme 2021-2027 between the Republic of Bulgaria and the Republic of North Macedonia as well as of the Cross-border Strategy for Integrated Territorial Development that lay the foundation for the implementation of PO5 under the Programme. EA identifies, describes and assesses:

- the likely significant effects on the environment of implementing the INTERREG-IPA III CBC Programme and the Cross-border Strategy for Integrated Territorial Development;

- the most important environmental, natural resource-related and climate change-related constraints bearing on the performance of the INTERREG-IPA III CBC Programme and the Territorial Strategy;

- the opportunities for the INTERREG-IPA III CBC Programme and the Territorial Strategy to contribute to enhancing the state of the environment, building climate resilience on the target territories and the population, and promoting low carbon development and the transition to the green economy.

The main output of the work on this contract is the Environmental Assessment Report (EAR) for the programme and for the Cross-border Strategy for Integrated Territorial Development (two reports in total). The EAR is the central part of the environmental assessment. It forms the main basis for monitoring the significant effects of the implementation of the INTERREG-IPA III CBC Programme and the Territorial Strategy. All content-related, procedural, methodological and chronological aspects of implementing the EA are stipulated in the Ordinance of the Ministry of Environment and Water for the conditions and the order for implementing environmental assessment of plans and programs. The Contractor must strictly follow them. Since the EA process and the EAR are both defined by the SEA Directive, a correct transposition and proper application of its provisions, both in content and procedure must appear in the contract outputs as well, to meet the requirement for sufficient quality.

### Geographical area to be covered

The Contractor shall perform the tasks in Sofia and in the eligible areas of the INTERREG - IPA III CBC Programme 2021-2027 between the Republic of Bulgaria and the Republic of North Macedonia.

### Target groups

Managing Authority, National Authority, Ministry of Environment and Water and its relevant competent authorising officers, relevant urban, local, regional authorities/bodies/stakeholders in the participating countries

## Specific work

Hereinafter, is presented a non-exhaustive list of the tasks to be undertaken in order for the Contractor to achieve the contract results:

1. The Contractor must participate in a kick-off and ongoing meetings, if necessary, with the Contracting Authority on contract implementation issues. The ongoing meetings may be initiated by both the Contractor Authority and the Contractor.

2. Preparation of notification for determination of the applicable environmental assessment procedure to be submitted to the competent authority in accordance with art. 8 (1) of the Ordinance for implementing environmental assessment of plans and programs;

3. Preparation of a written request for assessment of the need for environmental assessment (EA) to be submitted to the competent authority in accordance with art. 8a (1) of the Ordinance for implementing environmental assessment of plans and programs;

4. Preparation of an environmental assessment report for INTERREG-IPA III CBC Programme and for Cross-border Strategy for Integrated Territorial Development shall be in compliance with art. 16 and 17 of the Ordinance for implementing environmental assessment of plans and programmes. When elaborating the EARs, the Contractor must reflect the opinion of the competent authority on the assessment of the need and scope for environmental and compliance assessment. The content of the EARs must be in strict conformity with Chapter 3 of the Ordinance for implementing environmental assessment of plans and programs;

5. In case it is deemed necessary by the competent authority, the Contractor shall conduct compliance assessment of the INTERREG-IPA III CBC Programme and of the Cross-border Strategy for Integrated Territorial Development in accordance with the requirements of the Ordinance of the Ministry of Environment and Water on the conditions and procedures for assessment of the compliance of plans, programs, projects and investment proposals with the object and purposes of conservation of protected areas;

6. The Contractor shall organise according to Chapter 4 of the Ordinance for implementing environmental assessment of plans and programs, public consultations with stakeholders and third persons for whom there is probability to be affected by the INTERREG-IPA III Programme and the Cross-border Strategy for Integrated Territorial Development in the different stages of the programming, respectively of the EA.

7. The Contractor shall submit to the Contracting Authority the final draft versions of the EARs where results from the public consultations in Bulgaria and in North Macedonia are reflected. Results from the public consultations in the partner country shall be provided by the Contracting Authority/partner country;

8. The Contractor prepares for submission request/s for issuing an opinion on EA for the INTERREG-IPA III Programme and the Cross-border Strategy for Integrated Territorial Development to the competent body following the provisions of Chapter 5 of the Ordinance for implementing environmental assessment of plans and programs;

9. The Contractor shall revise the final draft versions of the EARs based on the feedback from the EC, and/or as a result of ongoing modifications of the relevant legal framework or of the draft programme/Cross-border Strategy for Integrated Territorial Development, if necessary. Afterwards, the Contractor submits the final version of the ERs to the Contracting Authority.

The Contractor must comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en).

Where appropriate and necessary, the Contractor shall provide maps, diagrams, charts, etc. giving a better visualisation of the ERs’ findings and conclusions. The maps, diagrams and any additional supporting graphical content should be presented as separate graphic files in appropriate format which will allow for further use by the Contracting authority.

The Contractor shall take into consideration the above listed tasks and requirements while preparing Annex III Organisation and Methodology as part of the technical offer. The Contractor must strictly follow the template (Annex III) from the Tender Dossier and prepare it in a manner demonstrating clear understanding of the contract.

## Project management

### Responsible body

The Contracting Authority (CA) is the Territorial Cooperation Management Directorate within the Ministry of Regional Development and Public Works of the Republic of Bulgaria, in its capacity of Managing Authority for INTERREG – IPA III Cross-border Programmes 2021-2027 and is responsible for conducting the current tender procedure, and for signing the service contract.

### Management structure

The effective management of the contract will be ensured by the Contracting Authority / Managing Authority, in close coordination with the National Authority of the INTERREG IPA III CBC programme.

### Facilities to be provided by the contracting authority and/or other parties

No facilities or equipment will be provided by the Contracting Authority.

# LOGISTICS AND TIMING

## Location

The tasks related to the preparation of the EARs shall be undertaken mainly at the seat of the Contractor. Public consultations and meetings with relevant institutions, if needed, shall be conducted in locations from the eligible areas of the contract (see p. 4.1.2) that allow for the fulfilment of the relevant contractor’s obligations, particularly those related to the public consultations. In addition to that, meetings at the premises of, or alternatively online meetings with, the Contracting Authority, shall be organized in Sofia.

## Start date & period of implementation of tasks

The intended start date is the date of the contract registration within the file system of the Ministry of Regional Development and Public Works and the period of implementation of the contract will be 12 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

Most of the period for implementation of individual tasks under this contract is determined by law, more precisely in the Ordinance for implementing environmental assessment of plans and programs. The table below presents indicative time schedule of the implementation of the contract:

| Action | Participation in a kick-off and ongoing meetings with the Contracting Authority on contract implementation issues |
| --- | --- |
| Indicative time schedule | Up to 7 days from the start of the contract for the kick-off meeting. Ongoing meetings shall be organized in a jointly agreed time and format |
| Action | Submission of inception report |
| Indicative time schedule | Up to 7 days from the start of the contract |
| Action | Preparation for submission to the competent authority of notifications for (1) determination of the applicable environmental assessment procedure, and for (2) determination of the need for compliance assessment |
| Indicative time schedule | Up to 14 days from the start of the contract |
| Action | Submission of interim reports and the first draft versions of EARs for the programme and the territorial strategy |
| Indicative time schedule | First interim report and first draft EAR – no later than 45 days after the Contracting Authority has sent the draft version of the INTERREG-IPA III CBC Programme, alternatively the Programme Intervention Logic document; Second interim report and first draft EAR - no later than 45 days after the Contracting Authority has sent the draft version of the Territorial Strategy to the Contractor; Third interim report and second draft EAR – no later than 14 days after the completion of the public consultations on the INTERREG-IPA III CBC Programme with reflected results from the consultations; Fourth interim report and second draft EAR - no later than 14 days after the completion of the public consultations on the Territorial Strategy with reflected results from the consultations; |
| Action | Preparation for submission of request for issuing an opinion on EA to the competent body |
| Indicative time schedule | Up to 5 days after the written consent of the Contracting Authority on each second draft EAR |
| Action | Submission of final draft EAR reports in Bulgarian and English and corresponding summary versions in both languages – one on the INTERREG-IPA III CBC Programme and one on the Territorial Strategy accompanied by issued positive opinion on the respective EAR. The final draft versions of the EARs shall reflect comments and conclusions from the issued positive opinions on the EAR as well as shall reflect ongoing modifications of the relevant legal framework, if needed. |
| Indicative time schedule | Up to 14 days after the receipt of the issued by the competent authority opinion on the relevant EAR |
| Action | Submission of revised final EARs, and their corresponding summary versions, for the programme and for the strategy, based on feedback from the EC and/or as a result of ongoing modifications of the draft programme/Cross-border Strategy for Integrated Territorial Development |
| Indicative time schedule | Up to 15 days after the receipt of comments of the Contracting Authority on each draft final EARs, but in any event no later than 15 days before the expiration date of the contract |

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The Contractor shall select and hire other experts as required according to the needs. The selection procedures used by the Contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

Expert 1: Team leader

Qualifications and skills

- University master degree (or equivalent) according to the requirements of article 83, para 2 of the Environmental Protection Act

- Solid knowledge of the requirements of the current Bulgarian and European environmental regulatory framework and EU regulatory framework.

General professional experience

- Minimum experience of 3 years required in fields related to elaboration of environmental related documents, reports and analyses, or monitoring and control of the execution of environmental plans/programmes and/or environmental impact assessment of projects.

Specific professional experience

- Experience as a Team Leader in projects.

Expert 2: Expert for environmental assessment for programme document between Republic of Bulgaria and Republic of North Macedonia

Qualifications and skills

- University master degree (or equivalent) according to the requirements of article 83, para 2 of the Environmental Protection Act;

- Solid knowledge of the requirements of the current Bulgarian and European environmental regulatory framework.

General professional experience

- Minimum experience of 2 years required in fields related to elaboration of environmental related documents, reports and analyses.

Specific professional experience

- Experience as an expert in projects/activities related to environmental assessment of plans/programmes and/or environmental impact assessment of projects.

Expert 3: Expert for environmental assessment for the Cross-border territorial strategy between Republic of Bulgaria and Republic of North Macedonia

Qualifications and skills

- University master degree (or equivalent) according to the requirements of article 83, para 2 of the Environment Protection Act ;

- Solid knowledge of the requirements of the current Bulgarian and European environmental regulatory framework.

General professional experience

- Minimum experience of 2 years required in fields related to elaboration of environmental related documents, reports and analyses.

Specific professional experience

- Experience as an expert in projects/activities related to environmental assessment of plans/programmes and/or environmental impact assessment of projects.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English in one original and electronic version:

- Inception Report of maximum 12 pages to be produced after 7 days from the start of the contract implementation. In the report, the contractor shall describe e.g. initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel. The contractor should proceed with his/her work unless the contracting authority sends comments on the inception report.

- Interim reports – four reports should be submitted.

- The first one – no later than 45 days after submission of the draft programme documents from contracting authority to contractor. The report should be maximum 25 pages and the contractor shall describe e.g. recent findings, progress in implementation, any difficulties encountered and to present as annexes the draft version of the EAR for the programme documents in English and Bulgarian, including corresponding summaries in both languages. The contractor should proceed with his/her work unless the contracting authority sends comments on the interim report.

- The second one – no later than 45 day after submission of the draft Integrated Territorial Strategy from the contracting authority to the contractor. The report should be maximum 25 pages and the contractor shall describe e.g. recent findings, progress in implementation, any difficulties encountered and to present as annexes the draft version of the EAR for the strategy in English and Bulgarian, including corresponding summaries in both languages. The contractor should proceed with his/her work unless the contracting authority sends comments on the interim report.

- The third one – no later than 14 days after the completion of the public consultations on the INTERREG-IPA III CBC Programme. The report should be maximum 25 pages and the contractor shall describe e.g. recent findings, progress in implementation, any difficulties encountered and to present as annexes a second draft version of the EAR for the programme in English and Bulgarian, including corresponding summaries in both languages. The second draft version of the EAR should reflect results from the public consultations. The contractor should proceed with his/her work unless the contracting authority sends comments on the interim report.

- The fourth one – no later than 14 days after the completion of the public consultations on the Territorial Strategy. The report should be maximum 25 pages and the contractor shall describe e.g. recent findings, progress in implementation, any difficulties encountered and to present as annexes a second draft version of the EAR for the strategy in English and Bulgarian, including corresponding summaries in both languages. The second draft version of the EAR should reflect results from the public consultations. The contractor should proceed with his/her work unless the contracting authority sends comments on the interim report.

Draft final report– up to 14 days after the receipt of the issued by the competent authority opinion on the relevant EAR. The report should be maximum 50 pages (main text, excluding annexes) and the contractor shall describe e.g. recent findings, progress in implementation, any difficulties encountered and to present as annexes final draft versions of the EARs on the programme and on the strategy in English and Bulgarian, including corresponding summaries in both languages. The final draft versions of the EARs shall reflect comments and conclusions from the issued positive opinions on the respective EAR as well as shall reflect ongoing modifications of the relevant legal framework, if needed.

- Important note: If the issued, by the competent authority, opinions on the EARs for the programme and for the territorial strategy become available in different time, the Contractor submits the draft final report twice - as a draft final report 1 and 2 where each of the final draft versions of the EARs (for the programme and for strategy) is annexed individually to the respective draft final report.

- Each draft final report (if their separation is needed) should be supplemented by an electronic version of the respective final draft EAR (for the programme and for the strategy) in English and Bulgarian.

Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 15 days after the receipt of comments of the Contracting Authority on each draft final EARs, but in any event no later than 15 days before the expiration date of the contract. The report shall contain a sufficiently detailed description of the different options to support an informed decision on the EARs. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

- The Final report shall be accompanied by revised final EARs of the programme and the strategy. The revised final EARs and corresponding revised final summary versions of EARs for the programme and for the strategy shall be based on the feedback from the EC and/or as a result of ongoing modifications of the relevant legal framework, or modification of the draft programme/Cross-border Strategy for Integrated Territorial Development. The summary versions shall include information on how the environmental considerations have been taken into account. The summaries have to be prepared in English and Bulgarian.

- The EARs have to be elaborated in compliance with the provision of the Ordinance for the condition and the order for implementing Ecological Assessment of Plans and Programmes, the Ordinance for the conditions and the order for implementing Ecological Assessment of Plans and Programmes and investment proposals with the subject and objectives of protection of protected areas and taking into account the Directive 2011/92/EU of the European Parliament and of the Council (as amended by Directive 2014/52/EU of the European Parliament and of the Council).

## Submission and approval of reports

The reports referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

The electronic versions of the reports referred to above must be additionally submitted to the Contracting Authority on the following address:

MINISTRY OF REGIONAL DEVELOPMENT AND PUBLIC WORKS

9 “Stefan Karazdja” Str.

1000 Sofia, Bulgaria

e-mail: e-mrrb@mrrb.government.bg

The Head of the Managing/Contracting Authority is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The successful implementation of the contract will be assessed based on the following indicators of achievement:

- An electronic version and hard copy of the revised final two EARs in English and Bulgarian;

- Submitted two revised final EARs that are fully compliant with relative legislation;

- Conducted public consultations covering the territory of the INTERREG-IPA III CBC Programme;

- Inception, four interim and two final reports approved by the Contracting Authority;

- An electronic version of summaries of the revised final two EARs in English and Bulgarian.

## Special requirements

During implementation of the contract, all national and regional anti-epidemiological measures imposed by the authorities must be respected.