ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	3

2.	OBJECTIVES & EXPECTED OUTPUTS	4

2.1.	Overall objective	4

“Providing logistics and organisation for events related to the implementation of INTERREG-IPA cross-border cooperation programmes”.	4

2.2.	Specific objective(s)	4

2.3.	Expected outputs to be achieved by the contractor	4

3.	ASSUMPTIONS & RISKS	5

3.1.	Assumptions underlying the project	5

3.2.	Risks	5

4.	SCOPE OF THE WORK	5

4.1.	General	5

4.2.	Specific work	6

4.3.	Project management	14

5.	LOGISTICS AND TIMING	15

5.1.	Location	15

5.2.	Start date & period of implementation of tasks	15

6.	REQUIREMENTS	15

6.1.	Staff	15

6.2.	Office accommodation	16

6.3.	Facilities to be provided by the contractor	16

6.4.	Equipment	16

7.	REPORTS	16

7.1.	Reporting requirements	16

7.2.	Submission and approval of reports	17

8.	MONITORING AND EVALUATION	17

8.1.	Definition of indicators	17

# BACKGROUND INFORMATION

## Partner country

Republic of Bulgaria, Republic of Turkey, Republic of Serbia and the Republic of North Macedonia.

## Contracting authority

Directorate “Territorial Cooperation Management” (Directorate TCM) within the Ministry of Regional Development and Public Works (MRDPW) of the Republic of Bulgaria, Managing Authority of the Interreg-IPA Cross-border cooperation Programmes Bulgaria-Turkey, Bulgaria-Serbia and Bulgaria – North Macedonia.

## Country background

Territorial Cooperation Management Directorate, in its capacity of Managing Authority (MA) for the Interreg-IPA Cross-border cooperation Programmes Bulgaria - Turkey, Bulgaria - North Macedonia and Bulgaria - Serbia, is directly responsible for the overall management of the programmes, including the implementation of their communication strategies. The focus of the strategies falls on increasing the awareness about the programmes, their priorities, financing opportunities, as well as assisting the beneficiaries through information campaigns, partnership forums and other communication tools.

## Current situation in the sector

Directorate “Territorial Cooperation Management” (D TCM) at the Ministry of Regional Development and Public Works of the Republic of Bulgaria is designated as the Managing Authority of the IPA Cross-border Programmes between Republic of Bulgaria and Republic of Serbia, Republic of Bulgaria and Republic of Turkey and Republic of Bulgaria and the Republic of North Macedonia. D TCM is responsible for the overall implementation of the Programmes. Each year a number of events are organised for ensuring sound management and proper implementation: publicity events, meetings, trainings, etc.

Taking into consideration that in 2022 and 2023 IPA Cross-border Programmes for 2014-2020 and 2021-2027 periods are overlapping D TCM plans to organise the following types of events:

Monitoring Committee Meetings

- The Monitoring Committee (MC) is established under each Programme. It is a permanently acting bilateral partnership structure with a strategic decision-making role in the implementation of the Programme. The MC consists of representatives appointed by the two participating countries. Meetings of the MC will be organised in order decisions related to main Programme implementation issues are taken.

Technical meetings

- This type of event is organised to support of MC meetings or to address cases and issues where programme work requires it.

Training events

- The aim of the event is to increase the knowledge and skills of programme management and/or project implementation.

Strategy board meetings

- The Strategy board (SB) is established under each Programme. It is a permanently acting bilateral partnership structure with a role in implementing the Programme’s territorial strategies. The SB consists of representatives appointed by the two participating countries. Meetings of the SB will be organised in order for decisions related to main Programme implementation issues to be taken.

Info days

The purpose of such events is dissemination of information about the priorities and requirements of the call, as well as the procedures for submission and evaluation of proposals.

Partner search forum

Partner search forums will be organized in the eligible border area. The events will give the opportunity to all potential applicants to establish partnership relations in order to be able to realize future joint activities. During the forums the main principles and preconditions for establishment of successful and useful partnership will be presented.

Closing Conference

The overall objective of the conference is to present the results achieved during the 2014-2020 programming period and to present the plans for the 2021-2027 period. The conference will consist of several presentations/lectures, an awarding ceremony for the best Programme and project practices, and an exhibition of photographs displaying some of the most impressive results in the sphere of European Territorial Cooperation. This event will be held in Sofia.

EC Day

European Cooperation Days (EC Day) campaign was initiated in 2012 by INTERACT with the support of the European Commission, the European Parliament and the Committee of the Regions to celebrate people working together across borders. The main day of this Europe-wide campaign is 21st of September, but events take place throughout the whole month of September and even in October. The aim of this initiative coordinated by INTERACT is to communicate the achievements of European cooperation across borders to the general public.

## Related programmes and other donor activities

The following Programmes are related to the implementation of the events described in this document:

- Interreg-IPA CBC Bulgaria-Serbia Programme 2014-2020;

- Interreg-IPA CBC Bulgaria - Republic of North Macedonia Programme 2014-2020;

- Interreg-IPA CBC Bulgaria-Turkey Programme 2014-2020.

- Interreg-IPA CBC Bulgaria-Serbia Programme 2021-2027;

- Interreg-IPA CBC Bulgaria - Republic of North Macedonia Programme 2021-2027;

- Interreg-IPA CBC Bulgaria-Turkey Programme 2021-2027.

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective to which this action contributes is:

## “Providing logistics and organisation for events related to the implementation of INTERREG-IPA cross-border cooperation programmes”.

## Specific objective(s)

The specific objectives of this contract are as follows:

- Organised events under Interreg-IPA CBC Bulgaria-Serbia Programme 2014-2020 related its final phase and preparation for the 2021-2027 programming period.

- Organised events under Interreg-IPA CBC Bulgaria-Republic of North Macedonia 2014-2020 related its final phase and preparation for the 2021-2027 programming period.

- Organised events under Interreg-IPA CBC Bulgaria-Turkey Programme 2014-2020 related its final phase and preparation for the 2021-2027 programming period.

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

At least one of each type of event should be organised by the contractor in order to contribute to the overall and specific objectives.

Monitoring Committee Meetings

Technical meetings

Training events

Strategy board meetings

Info days

Partner search forum

Closing Conference

European Cooperation Day

- All specific event types expected to be organized are listed below in section “4.2. Specific work” consistent with specific frame of outputs to accomplish each of the event types (outcomes).

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- Clear understanding of the contract objectives and purposes on behalf of the Contractor;

- Timely information for the respective place and date of the events provided by the Contracting Authority as the schedule will be flexible;

- Full cooperation between the Contracting Authority and the Contractor in view to fulfil the tasks on time, with high quality and within the budget limitation.

## Risks

Potential risks to the successful implementation of the contract include:

- Lack of communication and logistical coordination between the Contractor and the Contracting Authority. In order to avoid this risk, the Contractor should be proactive and maintain continuous contact with the relevant representatives of the Contracting Authority.

- Insufficient quality of the services provided by the Contractor. In order to avoid this risk the Contractor should use the most reliable and experienced staff/service providers at his disposal.

- Possible new restrictions on the organization of events during the autumn and winter months, due to complications in the country/countries related to the spread of COVID-19 or other pandemic or endemic viruses.

# SCOPE OF THE WORK

## General

### Description of the assignment

The assignment includes all necessary services that the Contractor shall carry out for the overall logistical coordination and the organization of the events mentioned in section “4.2. Specific work”. Each event has to be organized separately, at different dates and in different places on the territory of the respective partnering country. For each event, the Contractor will have to provide a variety of professional services, such as transport and accommodation arrangements for the relevant participants, rent of conference hall for the events, catering for participants and guests, moderation and photo services, etc.

The exact dates and venues as well as the number of participants of the listed below events will be determined by the Contracting authority in due time before the respective event in order for the Contractor to be able to ensure transport, accommodation, catering and other related services. In case of catering services, the Contractor shall provide the Contracting authority with three alternative offers of menus. In case of accommodation service – at least two options fulfilling the listed requirements shall be proposed in advance (if there are possible options).

The Contracting authority reserves the right to make changes in the provisionally requested services with the written consent of the Contractor.

### Geographical area to be covered

Geographical area to be covered is the eligible area of the three Interreg-IPA CBC Programmes managed by Bulgaria.

### Target groups

Representatives of various national, regional and local institutions/organisations involved in the implementation of the Programmes; potential applicants and project beneficiaries, representatives of the national and regional media and general public.

## Specific work

The selected Contractor shall provide the following services related to the envisaged events.

General requirements

CONFERENCE HALL

- A conference hall or a big meeting room arranged in appropriate style, ensuring enough space for convenient work of the participants. The Contractor should coordinate in advance the arrangement of the hall (U-shape, theatre, classroom etc.) with the Contracting Authority;

- A room (lounge, reception room etc.) for coffee breaks /lunch located close by the conference room;

- Wireless Internet access in the meeting room for all participants of the event;

- A multimedia projector and a white screen for displaying presentations (the size should be enough for the space of the hall to ensure comfort visibility for every participant, but not less than 2x3 m.); additional screen/monitor (size 55’) arranged in the meeting room for events for up to 200 participants;

- Audio equipment for the entire duration of the event: 1) for MC and Strategy board meetings: 1 microphone per 2 participants to be arranged on the tables for the chairman, presenters and members; 2) for the remaining type of events: microphone per 2 participants to be arranged on the tables for the chairman and speakers and mobile microphone for the participants;

- Audio record from the event;

- A technician in charge of providing all the above-mentioned IT/technical equipment and ensuring that it functions correctly during the entire period of the meeting;

- Possibility to copy and print documents;

CATERING

- Mineral water served in bottles or glasses during the meeting in the conference hall,

- “Coffee break” including at least: 0.5 l. water, 0.25 l. juice, coffee, tea, biscuits and/or snacks (min. 100 gr. per person), fruits, etc.;

- “Buffet lunch” - min. 550 gr. per person including a choice of meat/fish/vegetarian hot and cold dishes, a choice of desserts, plus 0.5 l. water, coffee, tea;

- “Lunch pack” including a choice of bottle of mineral water 0.5 l., 0.25 l. juice , coffee, tea, biscuits and/or snacks (min. 100 gr. per person), sandwiches (min. 250 gr. per person);

- Dinner including non-alcoholic drinks – two types per person (water 0.5 l. bottle and 0.25 l. juice), salad (200 gr. per person), hors d’oeuvre (200 gr. per person), main meat meal (250 gr. Per person), dessert (100 gr. per person), tea, choice of soft drinks;

- The catering services should include professional staff for serving as well as ensuring special catering tables (in case such are not available at the venue).

ACCOMODATION AND TRANSPORTATION

- Accommodation in the same hotel as of the venue of the event (or in another at least 4 stars hotel in walking distance from the venue of the event) - for 1 night, single occupancy, breakfast included, for the MC voting members and MA/JS staff.

- Еxceptionally, if a 4-star hotel is not available at the location of the event, the contractor can propose a lower category hotel – 3 stars, or of the highest rank in the location.

- Transport of indicated number of persons from MC voting members and MA staff from Sofia to the place of the venue and back; it should be ensured that the bus/minibus that is used for the transportation is not older than 2009 model, air conditioned.

Type of events to be organised:

### Monitoring Committee Meetings

The Monitoring Committee (MC) is established under each Programme. It is a permanently acting bilateral partnership structure with a strategic decision-making role in the implementation of the Programme. The MC consists of representatives appointed by the two participating countries. Meetings of the MC will be organized in order decisions related to main Programme implementation issues to be taken.

#### Monitoring Committee Meetings in Bulgaria “Basic” type.

The contractor shall ensure the following:

- Conference hall for 4 hours for up to 60 participants;

- Catering services: 1 „Coffee break” and 1 “Buffet lunch” for up to 60 participants.

- Accommodation for up to 5 MA/JS staff for 1 overnight;

- Transportation of up to 15 persons - members of MC/MA/JS from Sofia to the place of the meeting (up to 150 km) and back to Sofia.

#### Monitoring Committee Meetings in Bulgaria “Sofia” type.

This type of MC will be held at the Conference hall of the MRDPW.

The contractor shall ensure the following:

- Catering services: 1 „Coffee break” and 1 “Buffet lunch” for up to 60 participants;

#### Monitoring Committee Meetings in Bulgaria “Long travel type”.

The contractor shall ensure the following:

- Conference hall for 4 hours for up to 60 participants;

- Catering services: 1 „Coffee break” and 1 “Buffet lunch” for up to 60 participants;

- Accommodation for up to 5 MA/JS staff for 1 overnight;

- Transportation of up to 15 persons - members of MC/MA/JS from Sofia to the place of the meeting (up to 400 km) and back to Sofia.

### Technical meetings

This type of event should be organized to support the MC meetings or to address cases and issues where programme work requires it.

#### Technical Meetings in Bulgaria “Basic” type

The contractor shall ensure the following:

- Conference hall for 4 hours for up to 15 participants;

- Catering services: 1 „Coffee break” and 1 “Buffet lunch” for up to 15 participants;

- Accommodation for up to 5 MA/JS staff for 1 overnight;

- Transportation of up to 5 MA/JS staff from Sofia to the place of the meeting (up to 150 km) and back to Sofia.

#### Technical Meetings in Bulgaria “Sofia” type

This type of Technical Meeting will be held at the Conference hall of the MRDPW.

The contractor shall ensure the following:

- Catering services: 1 „Coffee break” and 1 “Buffet lunch” for up to 15 participants.

#### Technical Meetings in Bulgaria “Long travel” type

The contractor shall ensure the following:

- Conference hall for 4 hours for up to 15 participants;

- Catering services: 1 „Coffee break” and 1 “Buffet lunch” for up to 15 participants;

- Accommodation for up to 5 MA/JS staff for 1 overnight;

- Transportation of up to 5 MA/JS staff from Sofia to the place of the meeting (up to 400 km) and back to Sofia.

### Training events:

#### Trainings for the Strategy board in Bulgaria “Basic” type

The aim of the event is to increase Strategy board members’ knowledge and skills for good management and to present good practices in project selection. The training will take place before the work of the Strategy board starts.

The contractor shall ensure the following:

- Conference hall for 4 hours for up to 40 participants;

- Catering services: 1 „Coffee break” and 1 “Buffet lunch” for up to 40 participants;

- Accommodation for up to 5 MA/JS staff for 1 overnight;

- Transportation of up to 15 SB/MA/JS staff from Sofia to the place of the meeting (up to 200 km) and back to Sofia.

#### Trainings for the Strategy board in Bulgaria “Long travel” type

The contractor shall ensure the following:

- Conference hall for 4 hours for up to 40 participants;

- Catering services: 1 „Coffee break” and 1 “Buffet lunch” for up to 40 participants;

- Accommodation for up to 5 MA/JS staff for 1 overnight;

- Transportation of up to 15 SB/MA/JS staff from Sofia to the place of the meeting (up to 400 km) and back to Sofia.

#### Trainings for the Strategy board in Bulgaria “Sofia” type.

This type of training will be held at Conference hall of the CA (MRDPW).

- Catering services: 1 „Coffee break” and 1 “Buffet lunch” for up to 40 participants.

#### Two-days Annual workshop for MA staff

The aim of the event is to address and solve problems in the everyday team work and to improve communication skills in the context of public administration units.

The contractor shall ensure the following:

- Conference hall for 4 hours for up to 70 participants;

- Catering services: 2 times „Coffee break”, 2 times “Buffet lunch” and 2 dinners for up to 70 participants;

- Accommodation for up to 70 participants for 2 overnight;

- Transportation of up to 70 MA staff from Sofia to the place of the meeting (up to 250 km) and back to Sofia.

### Strategy board meetings

These types of events will be organised for Strategy board in order to make decisions related to the main Programmes implementation issues to be taken.

#### Strategy board meetings in Bulgaria “Basic” type

The contractor shall ensure the following:

- Conference hall for up to 8 hours for up to 40 participants;

- Catering services: 1 „Coffee break” and 1 “Buffet lunch” for up to 40 participants;

- Accommodation for up to 5 MA/JS staff for 1 overnight.

- Transportation of up to 15 SB/MA/JS staff from Sofia to the place of the meeting (up to 150 km) and back to Sofia;

#### Strategy board meetings in Bulgaria “Long travel” type

The contractor shall ensure the following:

- Conference hall for up to 8 hours for up to 40 participants;

- Catering services: 1 „Coffee break” and 1 “Buffet lunch” for up to 40 participants;;

- Accommodation for up to 5 MA/JS staff for 1 overnight.

- Transportation of up to 15 SB/MA/JS staff from Sofia to the place of the meeting (up to 400 km) and back to Sofia;

4.2.3.3. Strategy board meetings in Bulgaria “Sofia” type

This type of meeting will be held at Conference hall of the CA (MRDPW).

- Catering services: 1 „Coffee break” and 1 “Buffet lunch” for up to 40 participants;

### Info days

The purpose of such events is dissemination of information about the priorities and requirements of the call, as well as the procedures for submission and evaluation of proposals.

#### Info days in Bulgaria “Basic” type.

The contractor shall ensure the following:

- Conference hall for 4 hours for up to 80 participants;

- Catering services: 1 „Coffee break” for up to 80 participants;

- Accommodation for up to 5 MA/JS staff for 1 overnight.

- Transportation of up to 5 MA/JS staff from Sofia to the place of the meeting (up to 150 km) and back to Sofia;

#### Info days in Bulgaria “Long travel” type

The contractor shall ensure the following:

- Conference hall for 4 hours for up to 80 participants;

- Catering services: 1 „Coffee break” for up to 80 participants;

- Accommodation for up to 5 MA/JS staff for 1 overnight.

- Transportation of up to 5 MA/JS staff from Sofia to the place of the meeting (up to 400 km) and back to Sofia;

#### Info day in Bulgaria “Short” type.

The contractor shall ensure the following:

- Conference hall for 4 hours for up to 80 participants;

- Catering services: 1 „Coffee break” for up to 80 participants;

- Transportation of up to 3 MA staff from Sofia to the place of the meeting (up to 150 km) and back to Sofia.

#### Info days “Abroad” type

- Accommodation for up to 5 MA/JS staff for 1 overnight;

- Transportation of up to 5 MA/JS staff from Sofia to the place of the meeting (up to 200 km) and back to Sofia.

### Partner search forum

Partner search forums will be organized in the eligible border area. The events will give the opportunity to all potential applicants to establish partnership relations in order to be able to realize future joint activities. During the forums the main principles for establishment of a successful and useful partnership will be presented.

#### Partner search forum in Bulgaria “Basic” type

The contractor shall ensure the following:

- Conference hall for 4 hours for up to 150 participants;

- Catering services: 1 „Coffee break” for up to 150 participants;

- Accommodation for up to 5 MA/JS staff for 1 overnight.

- Transportation of up to 5 MA/JS staff from Sofia to the place of the meeting (up to 150 km) and back to Sofia;

#### Partner search forum in Bulgaria “Short” type

The contractor shall ensure the following:

- Conference hall for 4 hours for up to 150 participants;

- Catering services: 1 „Coffee break” for up to 150 participants;

- Accommodation for up to 3 MA staff for 1 overnight.

- Transportation of up to 3 MA staff from Sofia to the place of the meeting (up to 150 km) and back to Sofia;

#### Partner search forum “Abroad” type

- Accommodation for up to 5 MA/JS staff for 1 overnight;

- Transportation of up to 5 MA/JS staff from Sofia to the place of the meeting (up to 200 km) and back to Sofia.

### Closing Conference

The overall objective of the conference is to present the results achieved during the 2014-2020 programming period. The conference will consist of several presentations/lectures, an awarding ceremony for the best Programme and project practices, and an exhibition of photographs* displaying some of the most impressive results in the field of European Territorial Cooperation. This event will be held in Sofia.

*photographs of the exhibition are not part of the service contract.

The contractor shall ensure the following:

- Conference hall for 4 hours for up to 200 participants;

- Catering services: 1 „Coffee break” for up to 200 participants and 1 “Buffet lunch” for 50 MA/NA/JS staff;

- Professional moderator for up to 4 hours;

- Professional photographer for up to 4 hours;

### EC Day abroad (Serbia / Turkey)

European Cooperation Days (ECD) campaign was initiated in 2012 to celebrate people working together across borders. The main day of this Europe-wide campaign is 21st of September, but events take place throughout the whole month of September and even in October. The aim of this initiative is to communicate the achievements of European cooperation across borders to the general public. The local events showcase how cross-border, transnational and interregional cooperation projects are reducing obstacles and disparities, while at the same time increasing cultural understanding and efficiency between European regions. Supported by the European Commission and the European Parliament, European Cooperation Day invites all Europeans again this year to get out and meet neighbours at one of the events showcasing project results or highlighting the importance of territorial cooperation.

The contractor shall ensure the following:

- Accommodation for up to 10 MA/JS staff for 1 overnight;

- Transportation of up to 10 MA/JS staff from Sofia to the place of the meeting (average up to 400 km) and back to Sofia;

- Catering services: 2 “Lunch pack” for up to 10 MA/JS staff.

The contractor must also comply with the latest Communication and Visibility Requirements for EU-funded external action, laid down and published by the European Commission. (See https://ec.europa.eu/international-partnerships/comm-visibility-requirements_en )

## Project management

### Responsible body

“Territorial Cooperation Management” Directorate at the Ministry of Regional Development and Public Works of the Republic of Bulgaria will be Contracting Authority for this contract.

The Contracting Authority is responsible for conducting the current tender procedure, signing the service contract and carrying out the overall management and control on the contract implementation.

The Contracting Authority will appoint a contact person/s who will be responsible on its behalf for communication with the Contractor – sending Requests for organisation of each event and approval of proposals of the contractor, where necessary.

The Contractor is expected to accordingly appoint a contact person/s responsible on its behalf for communication with the Contractor. The Contractor shall ensure that on each Requests for organisation of event a corresponding proposal is sent to The Contracting Authority within the necessary technical time before the envisioned date of the event.

### Management structure

### The Contractor is fully responsible for the quality and timely delivery of the contract results, according to the contractual provisions. In this respect, the Contractor shall ensure that the reports are delivered on time and the executed activities are in line with the current Terms of Reference and the regulatory framework requirements.

### Facilities to be provided by the contracting authority and/or other parties

For some type of events, named “Sofia” type – a conference hall of the MRDPW will be provided. In such cases, the Contractor will be informed of the details such as time, access, technical means and other.

# LOGISTICS AND TIMING

## Location

Operational base for the project is the Ministry of Regional Development and Public Works of the Republic of Bulgaria. The locations of the specific events will be specified by the Contracting Authority.

## Start date & period of implementation of tasks

The intended start date is 03.02.2023 and the period of implementation of the contract will be 9 months from this date, but not later than 15.11.2023. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

The exact dates of the events will be officially confirmed and communicated to the Contractor after signing the service contract and 10 days prior to each event.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The contractor shall select and hire other experts as required according to the needs. The selection procedures used by the contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative and secretarial provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English in one original and one electronic version:

- Inception Report of maximum 5 pages to be produced within one week from the start of implementation. In the report the contractor shall describe e.g. example of a composition of service preposition, any difficulties encountered or expected in addition to the work programme and staff travel. The contractor should proceed with his/her work unless the contracting authority sends comments on the inception report.

- Interim reports should be submitted no later than 7 working days after the end of each 3th month of implementation of the contract. Approval of interim report by the Contracting Authority will be a basis for interim payment under the contract.

Draft final report of maximum 10 pages (main text, excluding annexes). This report shall be submitted no later than one month before the end of the period of implementation of tasks.

Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 7 days after receipt of comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to support an informed decision on conclusions and clear evidences on the implementation of all requested services. The final report must be provided along with the corresponding invoice.

- Please, note that each event will be specifically assigned with assignment letter from the Contractor. Copy of those assignment letters shall be included in the Interim reports for the respective events organised trough the period and all of them should be included in the final report.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

In case comments arise, the project manager sends the report back in 7 working days deadline and the revised report is submitted by the Contractor again in 7 working days. In case the actual reported activities differ substantially from the corresponding assignment letter for the events and/or differ from the contractual provisions, the Contracting Authority reserves its right to not accept in full or partially a report.

In the absence of comments or approval by the project manager within 7 working days, the reports are deemed to be approved.

# MONITORING AND EVALUATION

## Definition of indicators

Organised 34 events summarized in 22 different types as specified in section “4.2. Specific work”.